## Gantt Chart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | [Project's title] |  |  |  |  | COMPANY NAME | [6 empty] | [Company's name]
PROJECT MANAGER |  | [Project Manager's name] |  |  |  |  | DATE | [6 empty] | 2018-03-12
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Define financial objectives and scope | Dung Nguyen | 2024-03-12 | 2024-03-15 | 3 | 100% | bar: WEEK 1 F to WEEK 2 T
1.1.1 | Project Charter Revisions | Kylie R | 2024-03-15 | 2024-03-18 | 3 | 100% | bar: WEEK 2 W to WEEK 2 R
1.2 | Identify key financial stakeholders | Pete S | 2024-03-15 | 2024-03-21 | 6 | 90% | bar: WEEK 2 W to WEEK 3 W
1.3 | Prepare an initial project charter and budget | Steve L | 2024-03-16 | 2024-03-22 | 6 | 40% | bar: WEEK 2 R to WEEK 3 R
1.4 | Stakeholders | Allen W | 2024-03-18 | 2024-03-22 | 4 | 70% | bar: WEEK 3 M to WEEK 3 R
1.5 | Guidelines | Malik M | 2024-03-19 | 2024-03-22 | 3 | 60% | bar: WEEK 3 T to WEEK 3 R
1.6 | Project Initiation | Malik M | 2024-03-23 | 2024-03-23 | 0 | 50% | bar: WEEK 3 F
2 | Financial Planning and Analysis
2.1 | Collect and validate financial data | Steve L | 2024-03-24 | 2024-03-28 | 4 | 22% | bar: WEEK 3 M to WEEK 3 W; WEEK 4 M to WEEK 4 R
2.2 | Perform cash flow and trend analysis | Allen W | 2024-03-29 | 2024-04-02 | 3 | 16% | bar: WEEK 4 F to WEEK 5 F
2.3 | Identify risks and develop mitigation strategies | Malik M | 2024-03-29 | 2024-04-06 | 3 | 0%
2.4 | Risk Management | Malik M | 2024-04-07 | 2024-04-07 | 0 | 0%
3 | Execution and Monitoring
3.1 | Implement financial strategies and action plans | Pete S | 2024-04-08 | 2024-04-11 | 4 | 0%
3.2 | Monitor actual cash flow and expenditure | Leon W |  |  | 0 | 0%
3.2.1 | Monitoring | Kylie R |  |  | 0 | 0%
3.2.2 | Forecasts | Kylie R |  |  | 0 | 0%
3.3 | Report deviations and adjust strategies accordingly | Pete S |  |  | 0 | 0%
3.3.1 | Chart Updates | Malik M |  |  | 0 | 0%
4 | Evaluation and Reporting
4.1 | Conduct final project analysis | Steve L |  |  | 0 | 0%
4.2 | Consolidate results into a comprehensive financial report | Allen W |  |  | 0 | 0%
4.3 | Present findings and lessons learned | Malik M |  |  | 0 | 0%
4.4 | Project Performance | Malik M |  |  | 0 | 0%